## SURVEY
Project -Final Inspection
| Project | JMS KANDA | [5 empty] | Date | 2025-09-04
| LOCATION : | PIPE SHOP 5 | [5 empty] | Report No | Final -001
| DWG NO |  |  |  | SYSTEM NO
S/NO | LINE NO | SPOOL NO | JOINT NO | MATERIAL -A | MATRIAL-B | JOINT TYPE | THICKNESS | WPS | WELDER | RESULT
1 | ADED-001-KDE-001 | SP001 | SW01 | PIPE -SS316 2" SCH10 HT NO:T324424 | FLANGE-SS316-2" 150# HT:K4924 | BW | 3.05 | SAWPS-089A | Y9893 | ACC
2 | ADED-001-KDE-001 | SP001 | SW02 | PIPE -SS316 2" SCH10 HT NO:T324424 | PIPE -SS316 2" SCH10 HT NO:T324424 | BW | 3.05 | SAWPS-089A | Y9893 | ACC
3 | ADED-001-KDE-001 | SP001 | SW03 | PIPE -SS316 2" SCH10 HT NO:T324424 | FLANGE-SS316-2" 150# HT:K4924 | BW | 3.05 | SAWPS-089A | Y9893 | ACC
4 | ADED-001-KDE-001 | SP001 | SW04 | PIPE -SS316 2" SCH10 HT NO:T324424 | PIPE -SS316 2" SCH10 HT NO:T324424 | BW | 3.05 | SAWPS-089A | Y9893 | ACC
5 | ADED-001-KDE-001 | SP001 | SW05 | PIPE -SS316 2" SCH10 HT NO:T324424 | FLANGE-SS316-2" 150# HT:K4924 | BW | 3.05 | SAWPS-089A | Y9893 | ACC
6
7
8
INSPECTION BY |  | SOME-PT |  |  | ABS |  |  | BP-G
NAME /SIGNATURE
DATE
Note on C7: adrian: HULL PIPE MECH ELEC SPC

## Sheet1
MAIN, EMERG, FWD DISTRIBUTION, MCC AND 24VDC PANEL SWITCHBOARD CLEANING
CATHODIC PROTECTION SYSTEM INSPECTION-YARD ARRANGE CAPAC SERVICE ENGR TO INSPECT ANODES AND REFERNCES CELLS
SPEED LOG TRANSDUCER RENEWAL- OWNER SUPPLY SPARE
REPLACEMENT OF THE FATHOMETER TRANSDUCER-ECHO SOUNDER TRANSDUCER REOLACE WITH OWNER SPARE
FORWARD MAST ELECTRICAL CABLE RENEWAL-RENEW ELECTRICAL CABLE TRANSIT ON FORWARD MAST
CARGO HOLD BILGE LEVEL ALARM FLOATS AND LIGHTING CONDUIT KICK PIPES-11 NOS FLOATS REMOVE FOR WASTED MOUNTING BRACKETS AND CONDUIT PIPES RENEW
Clarification: Motor Overhauls First Set
Galley Booster Heater Remove & Fit Back
Clarification: Motor Overhauls Second Set
CCTV Installation
Marine Growth Prevention System Inspection
Autronica Fire Detection System Renewal
2nd Deck Long’l Bhd Multi-Cable Transits
VISUAL INSPECTION FOR EMERGENCY FIRE PUMP SUCTION #01 SPL
VISUAL INSPECTION FOR CHEMICAL LAB DRAIN 1# SPLS
VISUAL INSPECTION FOR BOW THRUSTER VENT 4# SPLS